Planning and Budgeting Calendar for 2019/20

| Steps | Description of Activities in the Calendar | Expected date |
| --- | --- | --- |
| 1 | Budget indicative to be sent to the Provincial Executive and the Administration. If not available use the current allocation until the National Budgets are passed by the Assembly. | November 21st 2018 |
| 2 | Provincial Executive to determine policies and strategies to be undertaken in 2019/20 | December 10th 2018 |
| 3 | Based on this policy guidelines from the provincial executives, an allocation of indicative resources to the division should be made | December 15th 2018 |
| 4 | A training on the preparation of annual work plans & budget should be conducted including non devolved sectors of the PG | 21st Nov to 10th December 2018 |
| 5 | Actual preparations of the Annual work plans should begin. | From 16th December 2018 |
| 6 | Formulation of the budget for 2017/18 based on the annual work plans. | By 30th December 2018 |
| 7 | Review of the annual work plan and budget by the provincial executive | By 9th January 2019 |
| 8 | Incorporate comments from the provincial executive on the annual work plan and budget | By 15th January 2019 |
| 9 | Review of 2019/2020 annual work plans and budgets by the Ministry of provincial government and institutional strengthening/PGSP | 23rd January 2019 |
| 10 | Incorporation of Ministry comments | 23rd January to 15th February 2019 |
| 11 | Submission of final draft to the executive | 28th February 2019 |
| 12 | Provincial Public Accounts Committee to examine the budget | 1st – 8th March 2019 |
| 13 | Submission of final draft to the provincial assembly | 10th March 2019 |
| 14 | Provincial assembly appropriates the annual work plans and budgets and submit to the Minister to assent his signature | 20th March 2019 |
| 15 | Budget ready for spending | 1st April 2019 |