## Output report - FInancial
ANNEX 8 - QUARTERLY FINANCIAL REPORTING FORMAT - PCDF
FINANCIAL REPORTING FOR THE PROVINCIAL CAPACITY DEVELOPMENT FUND (PCDF) |  |  | Malaita Provincial Governament
Quarter: 2nd Quarter
2018-19 - Period ending on 30th September 2018 |  | BUDGET |  |  |  |  | RECEIPTS AND PAYMENTS |  |  |  |  | Total PCDF Expenditure
|  | NEW ANNUAL PCDF BUDGET | PCDF BUDGET b/f from previous FY | INITIAL BUDGET (appropriated) | REVISIONS / VIREMENTS | FINAL BUDGET | Q1 | Q2 | Q3 | Q4 | YEAR TO DATE (sum of Q1-Q4) | Oustanding Commitments at the time of reporting | Payments + Commitments |  | Balance Available
Section A: Annual Budget | [6 empty] | Section B Receipts and payments
PCDF Grant |  | 9147326 | 3382572.11 | 12529898.11 | 0 | 12529898.11
PCDF own contribution |  | 0 | 0 | 0 | 0 | 0
Total Budget |  | 9147326 | 3382572.11 | 12529898.11 | 0 | 12529898.11
|  |  | Section B: | Receipts (deposits into PCDF account) |  |  | Q1 | Q2 | Q3 | Q4 | Receipts
|  |  |  | PCDF Grant |  |  | 9147326 | 0 | 0 |  | 9147326
|  |  |  | PCDF committed/carried fwd |  |  | 3382572.11 | 0 | 0 | 0 | 3382572.11
|  |  |  | Bank Interest Earned |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Total Receipts |  |  | 12529898.11 | 0 | 0 | 0 | 12529898.11 | 0
Section C: Appropriated Investments/Projects (20%)
Project Name | Sector | [9 empty] | Total
I. Administration | [6 empty] | Q1 | Q2 | Q3 | Q4 | Payments | Commitments | Pmt + Cmt | % | Balance
Staff House 2 | Administration | 419173.7533 |  | 419173.7533 | 0 | 419173.7533 | 0 | 271346.69 | 0 |  | 271346.69 |  | 271346.69 |  | 147827.0633
Staff House 3 | Administration | 419173.7533 |  | 419173.7533 | 0 | 419173.7533 | 0 | 124358.14 | 0 |  | 124358.14 |  | 124358.14 |  | 294815.6133
Staff House 4 | Administration | 395695.0453 |  | 395695.0453 | 0 | 395695.0453 | 0 | 132393.48 | 0 |  | 132393.48 |  | 132393.48 |  | 263301.5653
Afio Sub Center | Administration | 300000 | 0 | 300000 | 0 | 300000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 300000
Lands Office Survey Equipment | Administration |  | 450000 | 450000 | 0 | 450000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 450000
Assembly Chambers Upgrade | Administration | 5422.648 | 226514.422 | 231937.07 | 0 | 231937.07 | 236937 | 0 | 0 |  | 236937 |  | 236937 |  | -4999.93
Fisheries Office Upgrade | Administration | 90000 | 0 | 90000 | 0 | 90000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 90000
Treasury Office refurbishment | Administration | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Total Administration | 1829465.2 | 676514.422 | 2505979.622 | 0 | 2505979.622 | 236937 | 528098.31 | 0 | 0 | 765035.31 | 0 | 765035.31 | 25.38% | 1740944.312
II. Service Delivery (75%) | [10 empty] | 0
Auki Market Fencing | Works, transport & Comm | 400000 | 0 | 400000 | 0 | 400000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 400000
SGS Jacob's ladder | Works, transport & Comm |  | 43096.66 | 43096.66 | 0 | 43096.66 | 21224.64 | 0 | 0 |  | 21224.64 |  | 21224.64 |  | 21872.02
Sulufoloa Market Building | Works, transport & Comm | 200000 | 0 | 200000 | 0 | 200000 |  | 0 | 0 |  | 0 |  | 0 |  | 200000
Rokotanikeni Market Houses | Works, transport & Comm | 130000 | 0 | 130000 | 0 | 130000 |  | 0 | 0 |  | 0 |  | 0 |  | 130000
Manawai Habour Market | Works, transport & Comm | 180000 | 0 | 180000 | 0 | 180000 |  | 0 | 0 |  | 0 |  | 0 |  | 180000
Onelafa Classroom (completion) | Education |  | 156313.15 | 156313.15 | 0 | 156313.15 |  | 116438.1416 | 0 |  | 116438.1416 |  | 116438.1416 |  | 39875.0084
Uhu Community High School Classroom | Education |  | 296179.6 | 296179.6 | 0 | 296179.6 |  | 26632.17 | 0 |  | 26632.17 |  | 26632.17 |  | 269547.43
Manakwai Community High | Education |  | 179290.58 | 179290.58 | 0 | 179290.58 |  | 0 | 0 |  | 0 |  | 0 |  | 179290.58
Gwaidegale CHS Dormitory | Education |  | 57784.88 | 57784.88 | 0 | 57784.88 | 57784.88 | 0 | 0 |  | 57784.88 |  | 57784.88 |  | 0
Busufo'osae Primary sch staff house | Education |  | 32925.9 | 32925.9 | 0 | 32925.9 |  | 0 | 0 |  | 0 |  | 0 |  | 32925.9
Luaniua CHS Classroom | Education |  | 8164 | 8164 |  | 8164 | 8164 |  |  |  | 8164
Busu Primary School Classroom | Education |  | 175942.52 | 175942.52 | 0 | 175942.52 | 163694.52 | 0 | 0 |  | 163694.52 |  | 163694.52 |  | 12248
Aimela Primary School Staff House | Education |  | 26179.6 | 26179.6 | 0 | 26179.6 |  | 26179.6 | 0 |  | 26179.6 |  | 26179.6 |  | 0
Maoro Christian Community School Admin & Library | Education |  | 29715.12 | 29715.12 | 0 | 29715.12 | 29715.13 | 0 | 0 |  | 29715.13 |  | 29715.13 |  | -0.01
Arnon Atomea CHS Classroom | Education |  | 88063.8 | 88063.8 | 0 | 88063.8 |  | 0 | 0 |  | 0 |  | 0 |  | 88063.8
Faiako CHS Classroom Building | Education | 757181.006 | 0 | 757181.006 | 0 | 757181.006 |  | 255240.5116 | 0 |  | 255240.5116 |  | 255240.5116 |  | 501940.4944
Faumamanu CHS Assembly Hall | Education | 650959.056 | 0 | 650959.056 | 0 | 650959.056 |  | 0 | 0 |  | 0 |  | 0 |  | 650959.056
Fo'ondo Primary School Classroom Building | Education | 757181.006 | 0 | 757181.006 | 0 | 757181.006 |  | 584778.5138 | 0 |  | 584778.5138 |  | 584778.5138 |  | 172402.4922
Gounabusu CHS Assembly Hall | Education | 182759.962 | 249837.151 | 432597.113 | 0 | 432597.113 |  | 0 | 0 |  | 0 |  | 0 |  | 432597.113
Hautahe Primary School classroom | Education |  | 341495 | 341495 | 0 | 341495 |  | 114859.3892 | 0 |  | 114859.3892 |  | 114859.3892 |  | 226635.6108
Kakara CHS Classroom | Education | 144715.332 | 291940.9335 | 436656.2655 | 0 | 436656.2655 |  | 0 | 0 |  | 0 |  | 0 |  | 436656.2655
Maka Primary School | Education | 757181.006 | 0 | 757181.006 | 0 | 757181.006 |  | 0 | 0 |  | 0 |  | 0 |  | 757181.006
Busu Water Tank Project | Water Supply & Sanitation | 4080 | 0 | 4080 | 0 | 4080 | 4080 | 0 | 0 |  | 4080 |  | 4080 |  | 0
Nanakimae Water tank and rain catchment | Water Supply & Sanitation | 400000 | 0 | 400000 | 0 | 400000 |  | 0 | 0 |  | 0 |  | 0 |  | 400000
Uruuru Rural Clinic | Health | 80020.14 | 0 | 80020.14 | 0 | 80020.14 |  | 0 | 0 |  | 0 |  | 0 |  | 80020.14
Gounatolo RHC Upgrade | Health | 560577.102 | 0 | 560577.102 | 0 | 560577.102 | 0 | 0 | 0 |  | 0 |  | 0 |  | 560577.102
Pipisu RHC Completion | Health | 505839.89 |  | 505839.89 | 0 | 505839.89 | 0 | 163793.44 | 0 |  | 163793.44 |  | 163793.44 |  | 342046.45
Foubaba Health Centre | Health | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
Pelau Coconut Crushing Mill | Agriculture | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
Kwalo Coconut Crushing Mill | Agriculture | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
Marapona Coconut Crushing Mill | Agriculture | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
Orotah Tabeu Crushing Mill | Agriculture | 200000 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 200000
Afio Fisheries Center Rehabilitation | Fisheries |  | 316092.428 | 316092.428 | 0 | 316092.428 | 0 | 175785.49 | 0 |  | 175785.49 |  | 175785.49 |  | 140306.938
Waihau Wildlife Conservation Research Centre Building | Environment & Conservation |  | 243907.76 | 243907.76 | 0 | 243907.76 | 243907.76 | 0 | 0 |  | 243907.76 |  | 243907.76 |  | -2.0955e-09
Mata Football Stadium Upgrade | Sports | 150000 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 150000
| Total Service Delivery | 6860494.5 | 2536929.0825 | 9397423.5825 | 0 | 9397423.5825 | 528570.93 | 1463707.2562 | 0 | 0 | 1992278.1862 | 0 | 1992278.1862 | 66.08% | 7405145.3963
III. Investment Servicing Costs (5%) |  | 457366.3 | 169128.6055 | 626494.9055 |  | 626494.9055 | 213603.05 | 43973.9 | 0 |  | 257576.95 | 0 | 257576.95 | 8.543% | 368917.9555
Total Investments |  | 9147326 | 3382572.11 | 12529898.11 | 0 | 12529898.11 | 979110.98 | 2035779.4662 | 0 | 0 | 3014890.4462 | 0 | 3014890.4462 |  | 9515007.6638
[13 empty] | PCDF Grant Utilized (%) | 24.06%
Prepared by : __________________________________________ Date: _____________________ | [6 empty] | Approved by: ______________________________________________ Date: ______________________

## Output report - Projects
OUTPUT REPORTING FORMAT FOR THE PG DEVELOPMENT PROJECTS INCLUDING PCDF
Malaita Province Quarterly Project Output Report
Reporting period |  | 2nd Quarter 2018/19
Position to fill the form |  | Mr. Rodney Fono
1. Reporting Table
Name of project | Planned Outputs (also Indicate whether it is New/Renovation) | MTS targeting (Nos 1-15)* | Ward Name and location | Approved Original Budget | Approved Revised Budget | Source of Funding PCDF | Other funding sources (OSR etc.) | Implementation Period (original planned completion versus/ new expected date ) | % Completed by end of quarter (with outputs) | Status (traffic light)* | Expenditures to date (end of quarter) | Procurement Method Used | Contractor | Estimated direct beneficiaries by gender |  | Est. Full time job created by invest-ment | Responsible Dept and person
[14 empty] | Male | Female
ADMINISTRATION
Staff House 2 | Auki- build a new 3 bedroom house | 12 | Auki ward 1 | 419173.7533 | 419173.7533 | PCDF |  | April 2018 - March 2019 | 64.73% | Green | 271346.69 | NCB | MARK BUILDERS CONSTRUCTION | 4 | 6 | 7 | Allen Bae
Staff House 3 | Auki- build a new 3 bedroom house | 12 | Auki ward 1 | 419173.7533 | 419173.7533 | PCDF |  | April 2018 - March 2019 | 29.67% | Green | 124358.14 | NCB | DAN QUALITY BUILDERS | 10 | 12 | 6 | Rodney Fono
Staff House 4 | Auki- build a new 3 bedroom house | 12 | Auki ward 1 | 419173.7533 | 419173.7533 | PCDF |  | April 2018 - March 2019 | 31.58% | Green | 132393.48 | NCB | TD BUILDERS | 4 | 4 | 8 | Allen Bae
Afio Sub Center | Afio-Renovation of 2 staff houses | 12 | Ward 23 | 300000 | 300000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB |  |  |  |  | Allen Bae
Lands Office Survey Equipment | A New survey Equipment | 4 | Auki ward 1 | 450000 | 450000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB |  |  |  |  | George Hoatamauri- Lands
Assembly Chambers Upgrade | Retention payment for completion of Assembly's Chambers | 12 | Auki ward 1 | 231937.07 | 231937.07 | PCDF |  | April 2018 - March 2019 | 100% | Green | 231937.07 | NCB | T-SMART CONSTRUCTION | 35 | 3 | 10 | Allen Bae
Fisheries Office Upgrade | Renovation of Auki Fisheries Office | 12 | Auki ward 1 | 90006.87 | 90006.87 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB |  |  |  |  | Allen Bae
Treasury Office refurbishment | Reburbishment of Treasury Office | 13 | Auki ward 1 | 200000 | 200000 | PCDF | MPGIS | April 2018 - March 2019 | 0% | Green |  | NCB |  | 35 | 5 | 20 | Allen Bae
WORKS,TRANSPORT & COMMUNICATION
Auki Market Fencing | Picket Fencing around the new market | 5 | Auki ward 1 | 400000 | 400000 | PCDF | 0 | April 2018 - March 2019 | 0% | Green |  | NCB |  |  |  |  | Allen Bae
SGS Jacob's ladder | Retention payment - Foot path connecting 3 communities | 3 | Radefasu Ward 29- Sakafou | 43096.66 | 43096.66 | PCDF | 0 | April 2018 - March 2019 | 49.25% | Green | 21224.64 | NCB | HIGHLANDERS CONSTRUCTION | 1000 | 800 | 20 | Allen Bae
Sulufoloa Market Building | Build a market to address gender balance to support women earn income | 3 | ward 14 Subobono/ Burianiasi | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Rokotanikeni Market Houses | Build a market to address gender balance to support women earn income | 3 | Ward 25-Tai | 130000 | 130000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Manawai Habour Market | Build a market to address gender balance to support women earn income | 3 | Auki ward 1 | 180000 | 180000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
EDUCATION
Onelafa Classroom (completion) | Completion of 6 blocks classroom | 9 | ward 14 Subobono/ Burianiasi | 156313.15 | 156313.15 | PCDF |  | April 2018 - March 2019 | 74.49% | Green | 116438.1416 | NCB | B2 LOGISTICS (CONTRACTOR) | 200 | 180 | 10 | Allen Bae
Uhu Community High School Classroom | Completion of 6 blocks classroom | 9 | ward 24 Mareho | 296179.6 | 296179.6 | PCDF |  | April 2018 - March 2019 | 8.992% | Green | 26632.17 | NCB | SUBS CONSTRUCTION | 90 | 150 | 20 | Allen Bae
Manakwai Community High | Completion of 6 blocks classroom | 9 | ward 8 Maluu | 179290.58 | 179290.58 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB | DAH_C CONSTRUCTION | 300 | 225 | 8 | Allen Bae
Gwaidegale CHS Dormitory | Retention payment for buidling completion | 9 | ward 28 Waneagu/ Sulanasina | 57784.88 | 57784.88 | PCDF |  | April 2018 - March 2019 | 100% | Green | 57784.88 | NCB | WOODSTORM CONSTRUCTION | 300 | 200 | 6 | Allen Bae
Busufo'osae Primary sch staff house | Retention payment for buidling completion | 9 | ward 29-Radefasu-Fa'arau | 32925.9 | 32925.9 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB | JB CONSTRUCTION | 200 | 150 | 12 | Allen Bae
Luaniua CHS Classroom | Retention payment for buidling completion | 9 | ward 31 Luaniua | 0 | 8164 | PCDF |  | April 2018 - March 2019 | 100% | Green | 8164 | NCB | DAN QUALITY HOME BUILDERS | 120 | 135 | 8 | Allen Bae
Busu Primary School Classroom | Additional draw to complete 4 blocks classroom | 9 | ward 30 Langalanga | 175942.52 | 175942.52 | PCDF |  | April 2018 - March 2019 | 93.04% | Green | 163694.52 | NCB | TT CONSTRUCTION | 200 | 168 | 6 | Allen Bae
Aimela Primary School Staff House | Retention payment for buidling completion | 9 | ward 2 Aimala | 26179.6 | 26179.6 | PCDF |  | April 2018 - March 2019 | 100% | Green | 26179.6 | NCB | AUDRIZ ENTERPRISES | 3 | 2 | 4 | Allen Bae
Maoro Christian Community School Admin & Library | Retention payment for buidling completion | 9 | ward 29-Radefasu-Fa'arau | 29715.12 | 29715.12 | PCDF |  | April 2018 - March 2019 | 100% | Green | 29715.13 | NCB | KB BUILDERS CONSTRUCTION | 300 | 350 | 10 | Allen Bae
Arnon Atomea CHS Classroom | Retention payment for buidling completion | 9 | ward 8 Maluu | 88063.8 | 88063.8 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB | DAH_C CONSTRUCTION | 220 | 180 | 8 | Allen Bae
Faiako CHS Classroom Building | New construction for 6 blocks classroom (2 storeys) | 9 | ward 3 Buma | 757181.006 | 757181.006 | PCDF |  | April 2018 - March 2019 | 33.71% | Green | 255240.5116 | NCB | UNIQUE ARCHITECT BUILDERS | 180 | 120 | 8 | Allen Bae
Faumamanu CHS Assembly Hall | Build Assesmbly Hall for staff and students | 9 | ward 16 Faumamanu/kwai | 560577.102 | 560577.102 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Fo'ondo Primary School Classroom Building | New construction for 6 blocks classroom (2 storeys) | 9 | ward 7 Foondo/ Gwaiau | 757181.006 | 757181.006 | PCDF |  | April 2018 - March 2019 | 77.23% | Green | 584778.5138 | NCB | VIRTUAL MAN ENGINEERING & CONSTRUCTION | 285 | 215 | 6 | Allen Bae
Gounabusu CHS Assembly Hall | Build Assesmbly Hall for staff and students | 9 | ward 18 Waneagu/ Taelanasina | 550000 | 550000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Hautahe Primary School classroom | Completion of 6 blocks classroom | 9 | ward 20 Are'are | 341495 | 341495 | PCDF |  | April 2018 - March 2019 | 33.63% | Green | 114859.3892 | NCB | WAPOPO CARPENTERS | 142 | 130 | 10 | Allen Bae
Kakara CHS Classroom | New construction for 6 blocks classroom (2 storeys) | 9 | ward 4 Fauabu | 510235.256 | 510235.256 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Maka Primary School | New construction for 6 blocks classroom (2 storeys) | 9 | ward 23 Asimae | 752816 | 752816 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
WATER SUPPLY AND SANITATION
Busu Water Tank Project | Retention payment for completion of project | 8 | ward 30 Langalanga | 4080 | 4080 | PCDF |  | April 2018 - March 2019 | 100% | Green | 4080 | NCB | TT CONSTRUCTION | 120 | 90 | 6 | Allen Bae
Nanakimae Water tank and rain catchment | New - 150 Sanitation facilities for 5 communities | 8 | Ward 19- Aiaisi- Manawai | 400000 | 512401 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB |  |  |  |  | Allen Bae
HEALTH AND MEDICAL
Uruuru Rural Clinic | Retention payment for completion of project | 8 | ward 12 Fouenda | 80020.14 | 80020.14 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB | MOUNTOL ENTERPRISES | 512 | 585 | 10 | Allen Bae
Gounatolo RHC Upgrade | Build a new clinic to replace the current run-down property | 8 | ward 13 Sulufou/ kwarande | 560577.102 | 560577.102 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Pipisu RHC Completion | Completion of double story clinic funded by other donors | 8 | ward 24 Mareho | 505839.89 | 505839.89 | PCDF |  | April 2018 - March 2019 | 32.38% | Green | 163793.44 | NCB | C.MAUSI CONSTRUCTION | 450 | 400 | 6 | Allen Bae
Foubaba Health Centre | Completion of double story clinic funded by other donors | 8 | Auki ward 1 | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
AGRICULTURE
Pelau Coconut Crushing Mill | Provision of mill for income generation | 2 | ward 32 Pelau | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Kwalo Coconut Crushing Mill | Provision of mill for income generation | 2 | ward 29-Radefasu-Fa'arau | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Marapona Coconut Crushing Mill | Provision of mill for income generation | 2 | ward 23 Asimae | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
Orotah Tabeu Crushing Mill | Provision of mill for income generation | 2 | ward 23 Asimae | 200000 | 200000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
FISHERIES AND MARINE
Afio Fisheries Center Rehabilitation | Completion of centre to provide income for fishermen | 2 | ward 22- Afio | 316092.428 | 316092.428 | PCDF |  | April 2018 - March 2019 | 55.61% | Green | 175785.49 | NCB | SMART BUILDING & JOINERY CONST | 400 | 400 | 7 | Allen Bae
ENVIRONMENT & CONSERVATION
Waihau Wildlife Conservation Research Center | Retention of payment for research centre completion | 11 | Ward 25-Tai | 243907.76 | 243907.76 | PCDF |  | April 2018 - March 2019 | 100% | Green | 243907.76 | NCB | AM GENERAL CONSTRUCTION | 1000 | 600 | 16 | Allen Bae
WOMEN,YOUTH & SPORTS
Mata Football stadium | Completion of an exisitng soccer pitch to engage youths in sports | 8 | Ward 21- Afio | 150000 | 150000 | PCDF |  | April 2018 - March 2019 | 0% | Green |  | NCB
2. Notes
* MTS = Medium Term Strategy . The 15 strategies in the MTS are shown below. Not all may relevant for at PG, and it is important that the PCDF investment menu is adhered with.
Medium Term Strategy 1: Reinvigorate and increase the rate of inclusive economic growth
Medium Term Strategy 2: Improve the environment for private sector development and increase investment opportunities for all Solomon Islanders.
Medium Term Strategy 3: Expand and upgrade weather resilient infrastructure and utilities focused on access to productive resources and markets and to essential services
Medium Term Strategy 4: Strengthen land reform and other programmes to encourage economic development in urban, rural and customary lands.
Medium Term Strategy 5: Alleviate poverty, improve provision of basic needs and increase food security
Medium Term Strategy 6: Increase employment and labour mobility opportunities in rural areas and improve the livelihoods of all Solomon Islanders.
Medium Term Strategy 7: Improve gender equality and support the disadvantaged and the vulnerable.
Medium Term Strategy 8: Ensure all Solomon Islanders have equitable access to quality health care; combat communicable and non-communicable diseases.
Medium Term Strategy 9: Ensure all Solomon Islanders can access quality education and the nation’s manpower needs are sustainably met.
Medium Term Strategy 10: Improve disaster and climate risk management including prevention, risk reduction, preparedness, response and recovery and adaptation as part of resilient development.
Medium Term Strategy 11: Manage the environment in a sustainable resilient way and effectively respond to climate change.
Medium Term Strategy 12: Efficient and effective public service with a sound corporate culture: The objective of this strategy is to enhance efficiency and effectiveness of public sector founded on principles of transparency, accountability, trustworthy and honesty.
Medium Term Strategy 13: Reduce Corruption and improve governance at national, provincial and community levels: The objective of this strategy is to reduce corruption within government institutions and to instil a sound corporate culture at all levels
Medium Term Strategy 14: Improve national unity, peace and stability at all levels:
The objective of this strategy is to achieve a united and stable society based on mutual respect of our diverse cultural heritage.
Medium Term Strategy 15: Improve national security, law and order and foreign relations: A healthy and productive society must have a high level of law and order.
3. Comments on status*
No. | Status | Comments
No1 | Yellow | All projects carry forward to 2018/2019 budget
No2 | Green | Project on track in all aspects
No3 | Red | All projects funds vire for completion of other projects including projects under the Admin Sector for Green House Renovation
| Orange | Aiaisi project incomplete
Activity Traffic Light Status
(Green, Yellow, Orange, Red – see notes)
GREEN (On track to be achieved on schedule. Does not require comment but you may choose to comment),YELLOW (Some concerns about achievement on schedule. For advice only
ORANGE (Significant concerns about achievement on schedule. Requires comment explaining rating, and is for management attention) RED (Off Track to be achieved on schedule. Requires comments explaining rating, mitigation strategies and management action)
Prepared by: ……………………………………………. (CPO) |  |  |  |  | Approved: …………………………………………………. (PS) |  |  |  |  | …………………………………………………….. (PTR)