## Sheet1 (2)
OUTPUT REPORTING FORMAT FOR THE PG DEVELOPMENT PROJECTS INCLUDING PCDF
Central Province Quarterly Project Output Report
Reporting period | 2nd Quarter 2018/2019
Position to fill the form | Chief Planning Officer - John Rapemora
1. Reporting Table
Name of project | Planned Outputs (also Indicate whether it is New/Renovation) | MTS targeting (Nos 1-15)* | Ward Name and location | Approved Original Budget | Approved Revised Budget | Source of Funding PCDF | Other funding sources (OSR etc.) | Implementation Period (original planned completion versus/ new expected date ) | % Completed by end of quarter (with outputs) | Status (traffic light)* | Expendi-tures to date (end of quarter) | Procurement Method Used | Contractor | Estimated direct beneficiaries by gender |  | Est. Full time job created by invest-ment | Responsible Dept and person
[14 empty] | Male | Female
ADMINISTRATION
New Premier's Residence | Premier's residence is completed (new) | 12 | Tulagi | 499380 | 0 | 499380 | 0 | Sept 2018 - March 2019 | 0% |  | 0 | NCB | Pending PTB award | 4 | 9 | 10 | Mr. John Rapemora
Admin office furniture | Office furniture procured and commissioned (new) | 12 | Tulagi | 50000 | 0 | 0 | 50000 | June 2018 - August 2018 | 0% |  | 0 | LCB | Pending PTB award | 12 | 8 | 10 | Mr. John Rapemora
R&M Staff house Q14 | Staff house fully repaired and occupied (R&M) | 12 | Tulagi | 100370 | 0 | 100370 | 0 | June 2018 - August 2018 | 47.2% |  | 47129 | NCB | Pending PTB award | 5 | 4 | 6 | Mr. Charles Sasaka
R&M Staff house Q22 | Staff house fully repaired and occupied (R&M) | 12 | Tulagi | 100000 | 0 | 0 | 100000 | June 2018 - August 2018 | 38.4% |  | 31870 | LCB | Pending PTB award | 4 | 6 | 7 | Mr. Charles Sasaka
R&M Staff house Q21 | Staff house fully repaired and occupied (R&M) | 12 | Tulagi | 143000 | 0 | 143000 | 0 | June 2018 - August 2018 | 44.2% |  | 51257 | NCB | Pending PTB award | 5 | 5 | 7 | Mr. Charles Sasaka
R&M govt building No. 3 | Staff house fully repaired and occupied (R&M) | 12 | Tulagi | 5120 | 0 | 5120 | 0 | 2018-01-01 | 100% |  | 5120 | Variation claim | PTB & Exco yet to approve variation | 5 | 6 | 6 | Mr. Charles Sasaka
TOTAL ADMINISTRATION |  |  |  | 897870 | 0 | 747870 | 150000 |  |  |  | 135376 |  |  | 35 | 38 | 46
WATER SUPPLY AND SANITATION
Tabana Water Supply | New water supply system installed (new) | 7, 8 | SW Gella | 79990 | 0 | 79990 | 0 | May 2018 - August 2018 | 0% |  | 0 | LCB | Pending PTB award | 30 | 50 | 5 | Mr. Charles Sasaka
Kiolen Water Tank | New water tanks procured & installed (new) | 7, 8 | Pavuvu | 80000 | 0 | 80000 | 0 | May 2018 - August 2018 | 0% |  | 0 | NCB | Pending PTB award | 30 | 25 | 5 | Mr. Charles Sasaka
Nukufero CHS Water Tank | New water tanks procured & installed (new) | 7, 8 | Pavuvu | 80000 | 0 | 80000 | 0 | May 2018 - August 2018 | 0% |  | 0 | NCB | Pending PTB award | 70 | 60 | 5 | Mr. Charles Sasaka
Tulagi ablution block | Completed construction of Tulagi ablution block (new) | 8 | Tulagi | 28000 | 0 | 28000 | 0 | Nov 2016 - March 2018 | 100% |  | 28000 | LCB | Northern builders | 670 | 658 | 12 | Mr. Charles Sasaka
TOTAL WATER SUPPLY & SANITATION |  |  |  | 267990 | 0 | 267990 | 0 |  |  |  | 28000 |  |  | 800 | 793 | 27
INFRASTRUCTURE
Feeder road - Market to Chamber | Completed construction of feeder road (new) | 3 | Tulagi | 950000 | 0 | 950000 | 0 | Aug 2018 - March 2019 | 0% |  | 0 | NCB (MTB) | Yet to be advertised | 1251 | 658 | 20 | Mr. Charles Sasaka
South Savo Community Hall | Variation claim is paid to contractor | 1, 5, 7 | South Savo | 12000 | 0 | 12000 | 0 | Nov 2016 - March 2018 | 100% |  | 12000 |  | PTB & Exco yet to approve variation | 750 | 900 | 15 | Mr. John Rapemora
TOTAL INFRASTRUCTURE |  |  |  | 962000 | 0 | 962000 | 0 |  |  |  | 12000 |  |  | 2001 | 1558 | 35
EDUCATION
Rara primary classroom | Completion of two-storey 4 blocks classroom (new) | 9 | NW Ngella | 131175 | 0 | 131175 | 0 | May 2018 - Sept 2018 | 90% |  | 0 | NCB | Awaiting PTB award | 230 | 120 | 10 | Mr. Charles Sasaka
Gumu primary classroom | Completion of two-storey 4 blocks classroom (new) | 9 | CE Ngella | 131175 | 0 | 131175 | 0 | May 2018 - Sept 2018 | 95% |  | 0 | NCB | Awaiting PTB award | 140 | 65 | 12 | Mr. Charles Sasaka
Vatilau CHS classroom | Completion of two-storey 4 blocks classroom (new) | 9 | SanVesta | 131175 | 0 | 131175 | 0 | Nov 2016 - March 2018 | 90% |  | 0 | NCB | Awaiting PTB award | 230 | 300 | 12 | Mr. Charles Sasaka
TOTAL EDUCATION |  |  |  | 393525 | 0 | 393525 | 0 |  |  |  | 0 |  |  | 600 | 485 | 34
AGRICULTURE
Hakama cattle fencing rehabilitation | Completed fencing of tourism historical sites (new) | 1, 2, 6 | SW Gella | 100000 | 0 | 0 | 100000 | July 2018 - Oct 2018 | 0% |  | 0 | LCB | Yet to be advertised | 120 | 150 | 8 | Mr. Frank Omelanga
TOTAL AGRICULTURE |  |  |  | 100000 | 0 | 0 | 100000 |  |  |  | 0 |  |  | 120 | 150 | 8
WOMEN DEVELOPMENT
WRC Fencing | Completed construction of new copra refinery milling shed (new) | 1, 2, 7 | Tulagi | 100000 | 0 | 0 | 100000 | Sept 2017 - March 2018 | 0% |  | 0 | LCB | Awaiting PTB award | 250 | 560 | 9 | Mr. Charles Sasaka
TOTAL WOMEN DEVELOPMENT |  |  |  | 100000 | 0 | 0 | 100000 |  |  |  | 0 |  |  | 250 | 560 | 9
ASSEMBLY
Assembly recreational hut | Completed construction of new recreational hall (new) | 12 | Tulagi | 300000 | 0 | 0 | 150000 | Sept 2017 - Oct 2018 | 90% |  | 123750 | NCB | Awaiting PTB award | 120 | 78 | 12 | Mr. John Bosamata
Assembly audio & recording system | Completed installation of audio & recording systems | 12 | Tulagi | 100000 | 0 | 0 | 100000 | Sept 2017 - Oct 2019 | 100% |  | 82500 | NCB | Awaiting PTB award | 120 | 78 | 8 | Mr. John Bosamata
TOTAL ASSEMBLY |  |  |  | 400000 | 0 | 0 | 250000 |  |  |  | 206250 |  |  | 240 | 156 | 20
TOURISM
Preservation of Tulagi Historical Sites | Variation claim is paid to contractor | 1, 2, 6 | Tulagi | 15000 | 0 | 15000 | 15000 | 2018-02-01 | 100% |  | 15000 | Variation claim | PTB & Exco yet to approve variation | 758 | 658 | 8 | Mr. Simon Teva
TOTAL TOURISM |  |  |  | 15000 | 0 | 15000 | 15000 |  |  |  | 0 |  |  | 758 | 658 | 8
COMMERCE
Tulagi Mini Commercial Center | Mini commercial center is completed and commissioned | 2, 6 | Tulagi | 750000 | 0 | 750000 | 0 | Aug 2018 - March 2019 | 0% |  | 0 | NCB (MTB) | Yet to be advertised | 758 | 658 | 21 | Mr. John Rapemora
TOTAL COMMERCE & INVESTMENT |  |  |  | 750000 | 0 | 750000 | 0 |  |  |  | 0 |  |  | 758 | 658 | 21
ENVIRONMENT & CLIMATE CHANGE
Solid waste management - Tractor | Tractor is procured and commissioned | 3, 4 | Tulagi | 628500 | 0 | 628500 | 0 | Aug 2018 - Oct 2018 | 0% |  | 0 | NCB (MTB) | Yet to be advertised | 758 | 658 | 8 | Mr. Ben Tabo
Yandina fisheries centre sea defence | Sea defence structure completed and commissioned | 3, 10, 11 | Tulagi | 150000 | 0 | 0 | 150000 | Aug 2018 - March 2019 | 0% |  | 0 | NCB | Yet to be advertised | 730 | 599 | 10 | Mr. Talent
TOTAL ENVIRONMENT & CLIMATE CHANGE |  |  |  | 778500 | 0 | 628500 | 150000 |  |  |  | 0 |  |  | 1488 | 1257 | 18
GENERAL INVESTMENT SERVICING COSTS
DreamTec Designs - WRC Fencing Design | Fencing design & BOQ completed |  | Tulagi | 224467 |  | 224467 |  | April 2018 - March 2019 | 100% |  | 8000 |  | Service contracts signed | 3 | 2 | 3 | Mr. John Rapemora
Acess Plus - Project Sign Boards | Signboards are completed and installed at project sites |  | Tulagi |  |  |  |  | April 2018 - March 2019 | 100% |  | 9862.6 |  | Service contracts signed | 8 | 6 | 8 | Mr. John Rapemora
TOTAL GENERAL INVESTMENT SERVICES |  |  |  | 224467 | 0 | 224467 | 0 |  |  |  | 17862.6 |  |  | 11 | 8 | 11
GRAND TOTAL INVESTMENT |  |  |  | 4664885 | 0 | 3989352 | 765000 |  |  |  | 399488.6 |  |  | 7061 | 6321 | 237
2. Notes
* MTS = Medium Term Strategy . The 15 strategies in the MTS are shown below. Not all may relevant for at PG, and it is important that the PCDF investment menu is adhered with.
Medium Term Strategy 1: Reinvigorate and increase the rate of inclusive economic growth
Medium Term Strategy 2: Improve the environment for private sector development and increase investment opportunities for all Solomon Islanders.
Medium Term Strategy 3: Expand and upgrade weather resilient infrastructure and utilities focused on access to productive resources and markets and to essential services
Medium Term Strategy 4: Strengthen land reform and other programmes to encourage economic development in urban, rural and customary lands.
Medium Term Strategy 5: Alleviate poverty, improve provision of basic needs and increase food security
Medium Term Strategy 6: Increase employment and labour mobility opportunities in rural areas and improve the livelihoods of all Solomon Islanders.
Medium Term Strategy 7: Improve gender equality and support the disadvantaged and the vulnerable.
Medium Term Strategy 8: Ensure all Solomon Islanders have equitable access to quality health care; combat communicable and non-communicable diseases.
Medium Term Strategy 9: Ensure all Solomon Islanders can access quality education and the nation’s manpower needs are sustainably met.
Medium Term Strategy 10: Improve disaster and climate risk management including prevention, risk reduction, preparedness, response and recovery and adaptation as part of resilient development.
Medium Term Strategy 11: Manage the environment in a sustainable resilient way and effectively respond to climate change.
Medium Term Strategy 12: Efficient and effective public service with a sound corporate culture: The objective of this strategy is to enhance efficiency and effectiveness of public sector founded on principles of transparency, accountability, trustworthy and honesty.
Medium Term Strategy 13: Reduce Corruption and improve governance at national, provincial and community levels: The objective of this strategy is to reduce corruption within government institutions and to instil a sound corporate culture at all levels
Medium Term Strategy 14: Improve national unity, peace and stability at all levels:
The objective of this strategy is to achieve a united and stable society based on mutual respect of our diverse cultural heritage.
Medium Term Strategy 15: Improve national security, law and order and foreign relations: A healthy and productive society must have a high level of law and order.
3. Comments on status*
No. | Status | Comments
No1 | Yellow | Ex. The project has been delayed due to budget shortfall
No2 | Green | Project on track in all aspects
Etc. | Red
Orange
Activity Traffic Light Status
(Green, Yellow, Orange, Red – see notes)
GREEN (On track to be achieved on schedule. Does not require comment but you may choose to comment),YELLOW (Some concerns about achievement on schedule. For advice only
ORANGE (Significant concerns about achievement on schedule. Requires comment explaining rating, and is for management attention) RED (Off Track to be achieved on schedule. Requires comments explaining rating, mitigation strategies and management action)