# Monitoring report of provincial capital development projects for provinces

## CENTRAL PROVINCIAL GOVERNMENT PROJECTS

SECOND QUARTER 2018/2019 (JULY - SEPTEMBER 2018) REPORT ON THE IMPLEMENTATION AND MONITORING OF PCDF PROJECTS

|  | Project type | Ward No. | Start /end | Output achieved/expected | Output indicators | Outcome achieved or expected | Means of verifications | Project expenditure | Procurement Methods used | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Original budget | Actual expenditure (YTD) |  |  |
| NO. |  |  |  |  |  |  |  |  |  |  |  |
|  | FISCAL YEAR 2018/2019 – PERIOD APRIL TO JUNE 2018 |
|  | DEVELOPMENT PROJECTS – ADMINISTRATION |
| 1 | New Premier’s residence | 4 Tulagi | July 2018/ Mar 2019 | New executive house for the Premier of CPG is completed & handed over | 0 % completed | Improved living condition for the Premier of CP Assembly | Site visits by the project team | $499,380.00 | $0 | NCB – MTB to be involved – general contract | The PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
| 2 | Administration office furniture | 4 Tulagi | May 2018/ Mar 2019 | Office furniture are procured and used by CPG officers | 0 % completed | Improved working environment for CPG officers | Site visits by the project team | $50,000.00 | $24.00 | LCB – general contracting | The PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
| 3 | Staff house quarter 14 repairs | 4 Tulagi | July 2018/ Mar 2019 | Staff house is fully repaired and occupied by officers | 47.2% completed | Improved living condition for CPG officers | Site visits by the project team | $100,370.00 | $47,120.00 | NCB – general contracting | Procurement process was complied with. Contract of $114,252 was awarded to M Honi Builders & Plumbing and signed on 6/9/2018 |
| 4 | Staff house quarter 22 repairs | 4 Tulagi | July 2018/ Mar 2019 | Staff house is fully repaired and occupied by officers | 38 % completed | Improved living condition for CPG officers | Site visits by the project team | $100,000.00 | $31,870.00 | LCB – general contracting | Procurement process was complied with. Contract of $77,261 was awarded to HW Constructions and signed on 6/9/2018 |
| 5 | Staff house quarter 21 repairs | 4 Tulagi | July 2018/ Mar 2019 | Staff house is fully repaired and occupied by officers | 44 % completed | Improved living condition for CPG officers | Site visits by the project team | $143,000.00 | $51,257.00 | NCB – general contracting | Procurement process was complied with. Contract of $124,260 was awarded to Pacific Professional Builders and signed on 6/9/2018 |
| 6 | Government building House No. 3 | 4 Tulagi | April 2018 / June 2018 | Staff house is fully renovated and occupied by PG officials | 100% completed | Improved living conditions for CPG officers | Site visits by the project team | $5,120.00 | $5,120.00 | Variation claim – previous contract | Variation payment was approved by the PTB during their meeting on 22/7/2018 and payment has been issued |
| TOTAL DEVELOPMENT PROJECTS – ADMINISTRATION |  | $897,870.00 | $135,400.00 |  |  |
|  | DEVELOPMENT PROJECTS – INFRASTRUCTURE |
| 7 | Rehabilitation of feeder road – market to assembly chambers | 4 Tulagi | July 2018/ Mar 2019 | Feeder road is rehabilitated and used by CP Assembly and the public | 0 % completed | Improved road condition for conducive mobilization | Site visits by the project team | $950,000.00 | $0 | NCB – MTB to be involved – general contracting | The PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
| 8 | South Savo community hall | 13 South Savo | April 2018 / June 2018 | Community hall is completed and commissioned | 100% completed | Improved infrastructure for community social events | Site visits by the project team | $12,000.00 | $12,000.00 | Variation claim – previous contract | Variation payment was approved by the PTB during their meeting on 22/7/2018 and payment has been issued |
| TOTAL DEVELOPMENT PROJECTS - INFRASTRUCTURE |  | $962,000.00 | $12,000.00 |  |  |
|  | DEVELOPMENT PROJECTS – EDUCATION |
| 9 | Gumu primary school classroom – Phase II | 3 Central East Ngella | July 2018/ Mar 2019 | Completed 1 x 4 blocks two storey classroom building | 95 % completed | Improved learning environment and increased school enrolment as a result of the completion of the new 4 blocks classroom | On site visit by the project team | $131,175.00 | $0 | NCB – general contracting | Carried forward from 2017/2018. TEC has evaluated bids and now awaiting PTB award |
| 10 | Rara primary classroom – Phase II | 8 North West Ngella | July 2018/ Mar 2019 | Completed 1 x 4 blocks two storey classroom building | 90 % completed | Improved learning environment and increased school enrolment as a result of the completion of the new 4 blocks classroom | On site visit by the project team | $131,175.00 | $0 | NCB – general contracting | Carried forward from 2017/2018. TEC has evaluated bids and now awaiting PTB award |
| 11 | Vatilau CHS classroom – Phase II | 1 Sunfly / Buena Vista | July 2018/ Mar 2019 | Completed 1 x 4 blocks two storey classroom building | 90 % completed | Improved learning environment and increased school enrolment as a result of the completion of the new 4 blocks classroom | On site visit by the project team | $131,175.00 | $25,000.00 | NCB – general contracting | Carried forward from 2017/2018. TEC has evaluated bids and now awaiting PTB award |
| TOTAL DEVELOPMENT PROJECTS - EDUCATION |  | $393,525.00 | $25,000.00 |  |  |
|  | DEVELOPMENT PROJECTS – WATER & SANITATION |
| 12 | Completion of Tulagi township sanitation building | 4 Tulagi | July 2018/ Mar 2019 | New ablution block is completed and handed over to the CPG local council | 0 % completed | Improved public hygiene and sanitation | Site visits by the project team | $28,000.00 | $28,000.00 | Variation claim – for existing contract | Variation payment was approved by the PTB during their meeting on 22/7/2018 and payment has been issued |
| 13 | Tabana water supply rehabilitation | 5 South West Ngella | July 2018/ Mar 2019 | Water supply is fully rehabilitated and used by the communities | 0 % completed | Improved water supply and hygiene for the people of Tabana community | Site visits by the project team | $79,990.00 | $0 | LCB/NCB – general contracting | TEC has evaluated bids and now awaiting PTB award |
| 14 | Kiolen water supply rehabilitation | 10 Pavuvu | July 2018/ Mar 2019 | Water supply is fully rehabilitated and used by the communities | 0 % completed | Improved water supply and hygiene for the people of Kiolen community | Site visits by the project team | $80,000.00 | $0 | LCB/NCB – general contracting | TEC has evaluated bids and now awaiting PTB award |
| 15 | Nukufero CHS water tank project | 10 Pavuvu | July 2018/ Mar 2019 | Water tanks are procured & installed at Nukufero CHS | 0 % completed | Improved water supply and hygiene for the students & teachers of Nukufero CHS | Site visits by the project team | $80,000.00 | $0 | LCB/NCB – general contracting | TEC has evaluated bids and now awaiting PTB award |
| TOTAL DEVELOPMENT PROJECTS – WATER & SANITATION |  | $267,990.00 | $28,000.00 |  |  |
|  | DEVELOPMENT PROJECTS – COMMERCE & INVESTMENT |
| 16 | Completion of Tulagi mini commercial centre | 4 Tulagi | July 2018/ Mar 2019 | The commercial centre is completed and commissioned | 0 % completed | Improved access to commercial activities for CP and Tulagi citizens | Site visits by the project team | $750,000.00 | $0 | NCB – MTB to be involved – general contracting | PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
| TOTAL DEVELOPMENT PROJECTS – COMMERCE & INVESTMENT |  | $750,000.00 | $0 |  |  |
|  | DEVELOPMENT PROJECTS – WOMENS |
| 17 | Fencing of the new CP WRC | 4 Tulagi | May 2018/ Mar 2019 | Fencing is completed | 0 % completed | Improved security and safety of the WRC | Site visits by the project team | $100,000.00 $254,000.00 | $0 | LCB/NCB – general contracting | TEC has evaluated bids and now awaiting PTB award. PPDC during their meeting on 24/8/2018 agreed to increase budget to $254,000.00 due to reserve price |
| TOTAL DEVELOPMENT PROJECTS – WOMENS DEVELOPMENT |  | $100,000.00 | $0 |  |  |
|  | DEVELOPMENT PROJECTS – AGRICULTURE |
| 18 | Hakama cattle fencing & stock yard rehabilitation | 5 South West Ngella | May 2018/ Mar 2019 | Fencing is completed | 0 % completed | Improved management of PG cattle herd raised at the Hakama cattle farm | Site visits by the project team | $100,000.00 | $0 | LCB – general contracting | PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
| TOTAL DEVELOPMENT PROJECTS - AGRICULTURE |  | $100,000.00 | $0 |  |  |
|  | DEVELOPMENT PROJECTS – ENVIRONMENT & CLIMATE CHANGE |
| 19 | Yandina fisheries centre sea wall defence | 9 Banika | July 2018/ Mar 2019 | The sea wall is completed | 0 % completed | Provision of safety and resilience to effects to climate change and natural disasters | Site visits by the project team | $150,000.00 | $0 | NCB – general contracting | PPDC during their meeting on 23/8/2018, approved and recommended that this project is carried forward to 2019/2020 due to reduction on PCDF allocations |
|  | TOTAL DEVELOPMENT PROJECTS – ENVIRONMENT & CLIMATE CHANGE |  | $150,000.00 | $0 |  |  |
|  | CAPITAL PROJECTS – LOCAL COUNCIL |
| 20 | Solid waste management – tractor | 4 Tulagi | July 2018/ Mar 2019 | Tractor and all assorted fittings are procured and commissioned | Delivery of tractor & fittings to Tulagi local council | Improved solid waste management for improved health & hygiene | Site visits by the project team | $628,500.00 | $0 | NCB – MTB to be involved – LPO (goods only) | Project yet to be advertised. BOQ and Specifications obtained from suppliers. PPDC during their meeting on 24/8/2018 agreed to decrease budget to $237,160.00 due to reduced PCDF |
| TOTAL DEVELOPMENT PROJECTS – LOCAL COUNCIL |  | $628,500.00 | $0 |  |  |
| CAPITAL PROJECTS – TOURISM |
| 21 | Preservation of Tulagi historical sites | 4 Tulagi | April 2018 / June 2018 | Variation claim is paid to the contractor | 100% completed | Historical sites are conserved and increased number of tourist visitors to CP | Site visits by the project team | $15,000.00 | $15,000.00 | Variation claim – previous contract | Variation payment was approved by the PTB during their meeting on 22/7/2018 and payment has been issued |
| TOTAL DEVELOPMENT PROJECTS - TOURISM |  | $15,000.00 | 15,000.00 |  |  |
|  | CAPITAL PROJECTS – ASSEMBLY |
| 22 | Assembly chamber recreational hut | 4 Tulagi | May 2018/ Mar 2019 | Recreational hut is constructed and commissioned | 80 % completed | Improved working environment for assembly of CP and MPA’s | Site visits by the project team | $150,000.00 | $49,500.00 | NCB – general contracting | Existing contract with Twin Bros. This is a carried forward budget to an existing contract |
| 23 | Assembly chamber audio & recording system | 4 Tulagi | May 2018/ Mar 2019 | Audio & recording systems are installed and commissioned | 0 % completed | Effective delivery of assembly services | Site visits by the project team | $100,000.00 | $82,500.00 | NCB – general contracting (3rd time advertisement) | Direct invitation was made to three firms. PTB awarded a contract of $100,000.00 to Simon Gaetavem during their meeting on 22/7/2018 |
| TOTAL DEVELOPMENT PROJECTS - ASSEMBLY |  | $250,000.00 | $132,000.00 |  |  |
|  | GENERAL INVESTMENT SERVICING |
|  | General Comments There were twenty three (23) projects in the CPG 2018/2019 original capital budget. Twenty one (21) are funded by PCDF and CPG whilst two (2) are SIG funded projects. Out of the 21 PCDF funded projects, four projects are for variation payments only. These includes (i) South Savo community hall, (ii) Preservation of Tulagi historical sites, (iii) Staff building No.3 and (iv) Tulagi ablution block projects. Payments has since been made to the contractors following PTB approval on 22/7/2018. During the PPDC meeting on 24th August 2018, the PPDC also resolved to defer six (6) capital projects until 2019/2020. The reason was due to reduction in the total PCDF allocation to Central Provincial Government to only SBD $989,592.00. The six capital projects to be deferred were (i) Admin office furniture (ii) New Premier’s residence (iii) Feeder road: market to Assembly Chamber (iv) Tulagi mini-commercial centre, (v) Hakama cattle fencing and (vi) Yandina FC sea defence. Total budgetary allocation for procurement of a tractor for Solid Waste Management was also reduced due to the same reason. Therefore, CPG will be implementing only thirteen (13) capital projects in this FY, two (2) to be funded under SIG and 11 under PCDF and CPG. During the PTB meeting on 22/7/2018, the three (3) staff house projects for repair and maintenance has been approved for implementation to commence. PTB is now waiting for PCDF grants for 2018/2019 to be transferred to the CPG account before another seven (7) contracts are issued. The seven contracts has gone through the TEC and only awaiting PTB awards and announcements. Therefore, only the project for procurement of new tractor for solid waste management is yet to be advertised and evaluated. Critical issues that may affect timely completion of projects that the executive and the Ministry need to know Delay in effecting the procurement process 2018/2019 Up to the end of the second quarter of 2018/2019 FY, only three (3) contracts had been awarded. The provincial tender board has approved the commencement of these projects following transfer of CPG’s own contributions to the capital budget. The PTB has resolved to delay the award and announcement of the other projects due to (i) uncertainty on the actual PCDF allocations (ii) reduction in the total PCDF allocation. Recommendations for follow up before the next monitoring trip Information on PCDF allocations for Provincial Governments should be issued earlier to PG’s for their information and budgetary purposes. Using an indicative figure for budgetary purposes, and later reducing the budget figure by more than 50% is not reflective of good forward planning and might eliminate trust and confidence of politicians and ordinary people of Solomon Islands towards SIG and PCDF Prepared by: Date: Certified by: Date: ……………………………………… …………………………… ………………………………………. ………………………………. PCDA – CPG Provincial Secretary - CPG |